## GRC Dashboard
DOCUMENT 04 ¦ GRC MANAGEMENT DASHBOARD
Risk Treatment Plan & Statement of Applicability
Enterprise risks in scope | 60
Annex A controls | 93
Applicable controls | 93
Controls planned | 70
Controls partially implemented | 23
Treatment actions | 60
Management focus areas
1. | Close P1 treatment actions and validate residual risk.
2. | Validate control design and operating effectiveness with objective evidence.
3. | Establish the Control-to-Evidence Matrix as the next assurance artifact.
4. | Track overdue remediation and formal risk acceptance through management reporting.
5. | Review SoA applicability when scope, technology, regulatory or business context changes.

## Executive Summary
ABC TECHNOLOGIES PVT. LTD.
Document 04 ¦ Information Security Risk Treatment Plan & Statement of Applicability
Document ID | ABC-ISMS-RSK-004
Version | 1.0
Status | Proposed for Review & Approval
Owner | CISO Office
Process Owner | GRC / ISMS Manager
Classification | Confidential
Scope | 500-employee hypothetical
Review Cycle | Annual and upon material change
Annex A Controls | 93
Applicable Controls | 93
Risk Register Basis | 60 enterprise risks

## Risk Treatment Plan
Risk ID | Priority | Treatment Strategy | Treatment Outcome | Accountable Owner | Target | Status | Residual Risk Review | Evidence Expected
R-001 | P1 | Mitigate | Strengthen authorization, fraud monitoring and transaction integrity. | Application / Service Owner | TBD | Planned | Required | Control evidence + remediation closure
R-002 | P1 | Mitigate | Validate HA, recovery objectives and resilience testing. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-003 | P1 | Mitigate | Expand authorization testing, rate limiting and secure development gates. | Application / API Owner | TBD | Planned | Required | Control evidence + remediation closure
R-004 | P1 | Mitigate | Implement least privilege, PAM, strong authentication and access recertification. | IAM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-005 | P1 | Mitigate | Improve phishing resistance, endpoint hardening, encryption and device management. | IT Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-006 | P1 | Mitigate | Strengthen segmentation, cloud IAM, configuration assurance and resilience. | Cloud / Network Owner | TBD | Planned | Required | Control evidence + remediation closure
R-007 | P1 | Mitigate | Enforce risk-based vulnerability SLAs, patch compliance and exceptions. | Vulnerability Management Owner | TBD | Planned | Required | Control evidence + remediation closure
R-008 | P1 | Mitigate | Integrate security requirements, testing, secrets management and pipeline controls. | DevSecOps Owner | TBD | Planned | Required | Control evidence + remediation closure
R-009 | P1 | Mitigate | Implement immutable backups, restore testing and continuity arrangements. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-010 | P1 | Mitigate | Expand SIEM coverage, detection tuning, incident playbooks and evidence handling. | SOC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-011 | P1 | Mitigate | Implement classification, DLP, encryption, masking and secure deletion. | Information Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-012 | P1 | Mitigate | Strengthen JML, awareness, screening, confidentiality and insider-risk processes. | HR / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-013 | P2 | Mitigate | Tier suppliers, perform due diligence, control vendor access and contractual requirements. | Vendor Risk Owner | TBD | Planned | Required | Control evidence + remediation closure
R-014 | P2 | Mitigate | Strengthen entry controls, monitoring, environmental resilience and secure disposal. | Facilities / IT | TBD | Planned | Required | Control evidence + remediation closure
R-015 | P2 | Mitigate | Formalize ISMS governance, legal obligations, audit, CAPA and management reporting. | GRC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-016 | P2 | Mitigate | Strengthen authorization, fraud monitoring and transaction integrity. | Application / Service Owner | TBD | Planned | Required | Control evidence + remediation closure
R-017 | P1 | Mitigate | Validate HA, recovery objectives and resilience testing. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-018 | P2 | Mitigate | Expand authorization testing, rate limiting and secure development gates. | Application / API Owner | TBD | Planned | Required | Control evidence + remediation closure
R-019 | P1 | Mitigate | Implement least privilege, PAM, strong authentication and access recertification. | IAM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-020 | P1 | Mitigate | Improve phishing resistance, endpoint hardening, encryption and device management. | IT Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-021 | P2 | Mitigate | Strengthen segmentation, cloud IAM, configuration assurance and resilience. | Cloud / Network Owner | TBD | Planned | Required | Control evidence + remediation closure
R-022 | P2 | Mitigate | Enforce risk-based vulnerability SLAs, patch compliance and exceptions. | Vulnerability Management Owner | TBD | Planned | Required | Control evidence + remediation closure
R-023 | P1 | Mitigate | Integrate security requirements, testing, secrets management and pipeline controls. | DevSecOps Owner | TBD | Planned | Required | Control evidence + remediation closure
R-024 | P2 | Mitigate | Implement immutable backups, restore testing and continuity arrangements. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-025 | P1 | Mitigate | Expand SIEM coverage, detection tuning, incident playbooks and evidence handling. | SOC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-026 | P2 | Mitigate | Implement classification, DLP, encryption, masking and secure deletion. | Information Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-027 | P1 | Mitigate | Strengthen JML, awareness, screening, confidentiality and insider-risk processes. | HR / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-028 | P1 | Mitigate | Tier suppliers, perform due diligence, control vendor access and contractual requirements. | Vendor Risk Owner | TBD | Planned | Required | Control evidence + remediation closure
R-029 | P2 | Mitigate | Strengthen entry controls, monitoring, environmental resilience and secure disposal. | Facilities / IT | TBD | Planned | Required | Control evidence + remediation closure
R-030 | P1 | Mitigate | Formalize ISMS governance, legal obligations, audit, CAPA and management reporting. | GRC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-031 | P1 | Mitigate | Strengthen authorization, fraud monitoring and transaction integrity. | Application / Service Owner | TBD | Planned | Required | Control evidence + remediation closure
R-032 | P1 | Mitigate | Validate HA, recovery objectives and resilience testing. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-033 | P1 | Mitigate | Expand authorization testing, rate limiting and secure development gates. | Application / API Owner | TBD | Planned | Required | Control evidence + remediation closure
R-034 | P2 | Mitigate | Implement least privilege, PAM, strong authentication and access recertification. | IAM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-035 | P2 | Mitigate | Improve phishing resistance, endpoint hardening, encryption and device management. | IT Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-036 | P1 | Mitigate | Strengthen segmentation, cloud IAM, configuration assurance and resilience. | Cloud / Network Owner | TBD | Planned | Required | Control evidence + remediation closure
R-037 | P1 | Mitigate | Enforce risk-based vulnerability SLAs, patch compliance and exceptions. | Vulnerability Management Owner | TBD | Planned | Required | Control evidence + remediation closure
R-038 | P2 | Mitigate | Integrate security requirements, testing, secrets management and pipeline controls. | DevSecOps Owner | TBD | Planned | Required | Control evidence + remediation closure
R-039 | P2 | Mitigate | Implement immutable backups, restore testing and continuity arrangements. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-040 | P2 | Mitigate | Expand SIEM coverage, detection tuning, incident playbooks and evidence handling. | SOC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-041 | P2 | Mitigate | Implement classification, DLP, encryption, masking and secure deletion. | Information Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-042 | P2 | Mitigate | Strengthen JML, awareness, screening, confidentiality and insider-risk processes. | HR / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-043 | P1 | Mitigate | Tier suppliers, perform due diligence, control vendor access and contractual requirements. | Vendor Risk Owner | TBD | Planned | Required | Control evidence + remediation closure
R-044 | P1 | Mitigate | Strengthen entry controls, monitoring, environmental resilience and secure disposal. | Facilities / IT | TBD | Planned | Required | Control evidence + remediation closure
R-045 | P1 | Mitigate | Formalize ISMS governance, legal obligations, audit, CAPA and management reporting. | GRC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-046 | P1 | Mitigate | Strengthen authorization, fraud monitoring and transaction integrity. | Application / Service Owner | TBD | Planned | Required | Control evidence + remediation closure
R-047 | P2 | Mitigate | Validate HA, recovery objectives and resilience testing. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-048 | P2 | Mitigate | Expand authorization testing, rate limiting and secure development gates. | Application / API Owner | TBD | Planned | Required | Control evidence + remediation closure
R-049 | P2 | Mitigate | Implement least privilege, PAM, strong authentication and access recertification. | IAM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-050 | P2 | Mitigate | Improve phishing resistance, endpoint hardening, encryption and device management. | IT Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-051 | P2 | Mitigate | Strengthen segmentation, cloud IAM, configuration assurance and resilience. | Cloud / Network Owner | TBD | Planned | Required | Control evidence + remediation closure
R-052 | P2 | Mitigate | Enforce risk-based vulnerability SLAs, patch compliance and exceptions. | Vulnerability Management Owner | TBD | Planned | Required | Control evidence + remediation closure
R-053 | P3 | Mitigate | Integrate security requirements, testing, secrets management and pipeline controls. | DevSecOps Owner | TBD | Planned | Required | Control evidence + remediation closure
R-054 | P3 | Mitigate | Implement immutable backups, restore testing and continuity arrangements. | IT / BCM Owner | TBD | Planned | Required | Control evidence + remediation closure
R-055 | P1 | Mitigate | Expand SIEM coverage, detection tuning, incident playbooks and evidence handling. | SOC / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-056 | P1 | Mitigate | Implement classification, DLP, encryption, masking and secure deletion. | Information Security Owner | TBD | Planned | Required | Control evidence + remediation closure
R-057 | P3 | Mitigate | Strengthen JML, awareness, screening, confidentiality and insider-risk processes. | HR / CISO | TBD | Planned | Required | Control evidence + remediation closure
R-058 | P3 | Mitigate | Tier suppliers, perform due diligence, control vendor access and contractual requirements. | Vendor Risk Owner | TBD | Planned | Required | Control evidence + remediation closure
R-059 | P3 | Mitigate | Strengthen entry controls, monitoring, environmental resilience and secure disposal. | Facilities / IT | TBD | Planned | Required | Control evidence + remediation closure
R-060 | P3 | Mitigate | Formalize ISMS governance, legal obligations, audit, CAPA and management reporting. | GRC / CISO | TBD | Planned | Required | Control evidence + remediation closure

## Statement of Applicability
Control ID | ISO/IEC 27001:2022 Annex A Control | Theme | Applicable? | Applicability Rationale | Implementation State | Control Owner | Risk / Business Linkage | Evidence / Assurance Expectation
A.5.1 | Policies for information security | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.2 | Information security roles and responsibilities | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.3 | Segregation of duties | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.4 | Management responsibilities | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.5 | Contact with authorities | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.6 | Contact with special interest groups | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.7 | Threat intelligence | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.8 | Information security in project management | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.9 | Inventory of information and other associated assets | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.10 | Acceptable use of information and other associated assets | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.11 | Return of assets | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.12 | Classification of information | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.13 | Labelling of information | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.14 | Information transfer | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.15 | Access control | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.16 | Identity management | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.17 | Authentication information | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.18 | Access rights | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.19 | Information security in supplier relationships | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.20 | Addressing information security within supplier agreements | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.21 | Managing information security in the ICT supply chain | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.22 | Monitoring, review and change management of supplier services | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.23 | Information security for use of cloud services | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.24 | Information security incident management planning and preparation | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.25 | Assessment and decision on information security events | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.26 | Response to information security incidents | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.27 | Learning from information security incidents | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.28 | Collection of evidence | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.29 | Information security during disruption | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.30 | ICT readiness for business continuity | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.31 | Legal, statutory, regulatory and contractual requirements | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.32 | Intellectual property rights | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.33 | Protection of records | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.34 | Privacy and protection of PII | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.35 | Independent review of information security | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Partially Implemented | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.36 | Compliance with policies, rules and standards for information security | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.5.37 | Documented operating procedures | Organizational | Yes | Governance, risk, suppliers, cloud, incident response, continuity and compliance are material to the defined scope. | Planned | CISO / GRC | R-001 to R-060 ¦ Enterprise governance, supplier, cloud, incident, compliance and continuity exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.1 | Screening | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.2 | Terms and conditions of employment | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.3 | Information security awareness, education and training | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.4 | Disciplinary process | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.5 | Responsibilities after termination or change of employment | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Partially Implemented | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.6 | Confidentiality or non-disclosure agreements | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.7 | Remote working | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.6.8 | Information security event reporting | People | Yes | Workforce behavior, lifecycle and remote work materially affect information security. | Planned | HR / CISO | R-014, R-039, R-041, R-042, R-043 ¦ Human and workforce lifecycle exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.1 | Physical security perimeters | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.2 | Physical entry | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.3 | Securing offices, rooms and facilities | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.4 | Physical security monitoring | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Partially Implemented | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.5 | Protecting against physical and environmental threats | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.6 | Working in secure areas | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.7 | Clear desk and clear screen | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.8 | Equipment siting and protection | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.9 | Security of assets off-premises | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.10 | Storage media | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.11 | Supporting utilities | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Partially Implemented | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.12 | Cabling security | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Partially Implemented | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.13 | Equipment maintenance | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.7.14 | Secure disposal or re-use of equipment | Physical | Yes | Physical access, facilities and equipment can affect confidentiality, integrity and availability. | Planned | Facilities / IT | R-016, R-048, R-049, R-050, R-051 ¦ Physical and asset exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.1 | User endpoint devices | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.2 | Privileged access rights | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.3 | Information access restriction | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.4 | Access to source code | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.5 | Secure authentication | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.6 | Capacity management | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.7 | Protection against malware | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.8 | Management of technical vulnerabilities | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.9 | Configuration management | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.10 | Information deletion | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.11 | Data masking | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.12 | Data leakage prevention | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.13 | Information backup | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.14 | Redundancy of information processing facilities | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.15 | Logging | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.16 | Monitoring activities | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.17 | Clock synchronization | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.18 | Use of privileged utility programs | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.19 | Installation of software on operational systems | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.20 | Networks security | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.21 | Security of network services | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.22 | Segregation of networks | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.23 | Web filtering | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.24 | Use of cryptography | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.25 | Secure development life cycle | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.26 | Application security requirements | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.27 | Secure system architecture and engineering principles | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.28 | Secure coding | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.29 | Security testing in development and acceptance | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.30 | Outsourced development | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.31 | Separation of development, test and production environments | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.32 | Change management | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Partially Implemented | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.33 | Test information | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable
A.8.34 | Protection of information systems during audit testing | Technological | Yes | The technology estate, customer applications and cloud infrastructure require technical safeguards. | Planned | IT / Security / Engineering | R-001 to R-054 ¦ Technology, application, infrastructure, data and operational exposure | Policy / procedure, system configuration, access review, log, report, test result or audit evidence as applicable

## Methodology Notes
Topic | GRC Position
Purpose | Convert the enterprise risk register into accountable treatment decisions and establish the SoA baseline.
Treatment principle | Controls are selected based on risk, business context and applicable requirements, not as a mechanical checklist.
Applicability | Initial portfolio baseline marks all 93 Annex A controls applicable due to the broad scope.
Implementation state | Applicable does not mean implemented or effective. Evidence and assurance are required.
Risk acceptance | Acceptance must be explicit, authorized and periodically reviewed.
Evidence | Future Control-to-Evidence Matrix will connect each control to objective evidence.
Review triggers | Annual review plus material changes to scope, technology, threats, incidents, suppliers or regulatory requirements.
Portfolio disclaimer | ABC Technologies Pvt. Ltd. is hypothetical; dates, owners and states are illustrative until validated.